## Bugs & UX Issues
Enable Agents — Bugs & UX Issues
Rebuilt 2026-08-22 from a full-codebase audit (backend + frontend), cross-referenced against docs/context.md, docs/todo.md, and live verification on agents.enableyou.co. See the 'Architecture & Agent Quality' tab for the deeper 'are these really AI agents / do we need LangGraph or Temporal' assessment.
# | Agent/Feature | Issue | Why It's Confusing / User Impact | Severity | Root Cause (file:line) | Recommended Fix | Status | Date | Evidence/Notes
1 | Team Invitation | Invite email is not sent even though the UI shows an “Invitation Sent” toast. | A new teammate never gets their invite, and the inviter has no way to know it silently failed — they believe it worked. | Blocker | Not yet root-caused in code — earlier investigation only confirmed the existing send mechanism is wired correctly, not why delivery fails. Needs a real repro with SMTP/provider logs. | Add delivery confirmation (provider response, not just “request accepted”) before showing the success toast; log provider errors server-side. | Pending | 2026-07-25 | Toast says success while the underlying send fails — same failure shape as the Exec Assistant reminder-email bug that WAS root-caused (405/blocked route).
2 | Executive Assistant | Task reminder email is not sent to the team member. | Teammates miss reminders silently; no error is surfaced. | Major | Fixed — see corresponding 405 fix below. | — | Fixed & Deployed | 2026-07-25
3 | Data Insights | Chat bubble text is unreadable after asking a question (e.g. “what are the insights?”). | User can't read the AI's own answer. | Major | Chat bubble CSS — fixed earlier. | — | Fixed & Deployed | 2026-07-25
4 | Data Insights | Send arrow button sits in the middle of the chat input box instead of the right side. | Looks broken; users hesitate to click a misplaced control. | Minor | Chat input layout CSS — fixed earlier. | — | Fixed & Deployed | 2026-07-25
5 | Content Marketing Agent | The content assistant box keeps expanding vertically with no scrollbar, pushing the rest of the page down. | Page becomes unusable after a few messages. | Major | Missing max-height/overflow on chat panel — fixed earlier. | — | Fixed & Deployed | 2026-07-25
6 | General | Success/error toast messages have poor visual design. | Feedback is hard to notice or read. | Minor | Toast component styling — fixed earlier. | — | Fixed & Deployed | 2026-07-25
7 | Data Insights | In Visual Connections, the knowledge graph is not generated after a document is analyzed. | The one visual feature meant to make document analysis tangible for non-technical users just shows “No graph available” — looks broken even when analysis genuinely succeeded. | Major | frontend/src/agents/DataInsights.js getDocumentGraph() only builds a graph from liveEntitiesByType, which the backend (backend/agents/document_intelligence/models.py to_dict()) only populates when its entity-extraction step produced clean structured entity rows. A document can finish processing with only flat key facts and zero structured entities — graph silently stays empty even though the Key Facts tab (which already has a keyFacts fallback) has content. | Added a fallback: when liveEntitiesByType is empty, build the graph from getDocumentEntities() (same data already powering Key Facts) grouped by type. Implemented today. | Fixed - Pending Deploy | 2026-07-30
8 | Executive Assistant | While sending reminder emails to team members, the app says it cannot send emails (not allowed). | Blocks a core feature outright. | Blocker | nginx route whitelist regex on the VM didn't include /emails/send_via_gmail → 405. Fixed by adding a location /emails/ proxy block. | — | Fixed & Deployed | 2026-07-30
9 | Projects | Cancel button in the Create New Project dialog is misaligned and very wide. | Looks unpolished; button proportions feel broken. | Minor | Modal button CSS — fixed earlier. | — | Fixed & Deployed | 2026-07-30
10 | Executive Assistant | Long task names overflow outside the task cards on the Task Board. | Text spills over card edges, looks broken. | Minor | Kanban card CSS — fixed earlier. | — | Fixed & Deployed | 2026-07-30
11 | General | Selecting a project, navigating away, and coming back forgets the selection — no persistence. | User has to reselect their project constantly, feels like the app doesn't remember anything. | Major | No localStorage persistence for last-selected project — fixed earlier via ProjectSelector.js. | — | Fixed & Deployed | 2026-07-31
12 | Community Network | When network data is uploaded, the agent does not respond at all. | Looks completely broken/dead. | Blocker | Missing message-type handling — fixed earlier. | — | Fixed & Deployed | 2026-07-31
13 | Market Research | Entering product context, industry, and region and clicking Research Insights shows “Failed to generate requirements.” | Blocks the agent's core function entirely. | Blocker | Missing Authorization header on /generate-requirements and /search-google-businesses calls — fixed earlier as part of a systemic missing-auth-header sweep. | — | Fixed & Deployed | 2026-07-31
14 | Agents Assembly | The “Buy” button next to “Try Free” does nothing when clicked. | Dead button on a pricing CTA looks broken/untrustworthy. | Major | handleBuyModule now opens an informative message pointing to sales@enableagents.com, matching the product decision in docs/todo.md (#5: no silent failure, explain checkout is coming). | — | Fixed & Deployed | 2026-07-31
15 | Executive Assistant | Task input field is too small and doesn't wrap long text to the next line. | Typing a realistically long task title is unreadable while typing — text just scrolls sideways in a single-line box. | Major | frontend/src/agents/ExecutiveAssistantPage.js used a single-line <Input> for the quick-add task field. | Swapped to the existing <Textarea> component (rows=1, auto-grows up to 120px on input, Enter submits/Shift+Enter for a literal newline). Implemented today. | Fixed - Pending Deploy | 2026-08-03
16 | Executive Assistant | Long task descriptions get cut off with “...” on board cards; cards should expand to show full text. | Users can't read what the task actually says without opening it — defeats the purpose of a scannable board. | Major | frontend/src/styles/ExecutiveAssistantPage.css .kanban-card-title used white-space: nowrap + text-overflow: ellipsis with no expand affordance. | Changed to white-space: normal + overflow-wrap so the card grows to fit the full title (card container has no fixed height, so this is a clean fix, not a hack). Implemented today. | Fixed - Pending Deploy | 2026-08-03
17 | Market Research | Selecting Supplier Research or Customer Research after entering context/industry/region shows “Missing or invalid session”. | Blocks the agent's two core research modes entirely. | Blocker | Same root cause as the earlier /generate-requirements 401 — missing auth headers, just on the search path. Fixed in the same systemic sweep; this report predates that fix. | — | Fixed & Deployed | 2026-08-03 | Re-verified live on production 2026-08-22: 0 console errors on this exact flow.
18 | General | Welcome/Dashboard page needs a Create New Project button on the right, and 3 cards in order: projects, agents, workflows. | First screen a user sees after login didn't have an obvious “start here” action, and stat cards didn't reflect the platform's actual shape (projects weren't shown at all). | Major | frontend/src/pages/Dashboard.js had Active Workflows / Completed / AI Agents cards, no project count, no create-project CTA. | Added a real /api/projects count, reordered to Projects → AI Agents → Workflows, added a “+ Create New Project” button that deep-links to /projects?new=true (Projects.js now auto-opens the create modal on that param). Implemented and visually verified today. | Fixed - Pending Deploy | 2026-08-11
19 | Market Research | Clicking Extract Emails on customer research results shows “Unexpected token ‘<’, <html...”. | A working feature (email enrichment) becomes unusable for any realistically-sized lead list, with an error message that means nothing to a business user. | Blocker | backend enrich-businesses-with-emails processes every business serially (scrap.io + website scrape, up to ~20s worst case each) inside one request; nginx's 60s proxy_read_timeout cuts it off and returns an HTML error page, which the frontend then blindly calls response.json() on. | Backend: cap real per-request work at 25 new lookups, skip already-enriched businesses so retrying makes forward progress (MAX_BUSINESSES_PER_REQUEST in app.py). nginx: dedicated location for this route at 180s timeout. Frontend: no longer blind-parses error bodies as JSON; 504s get a plain-language “taking longer than expected, click again” message; partial success now says how many are left. Implemented today — this bounds the problem, but the underlying pattern (long synchronous per-item work in a request) should move to the existing Celery infrastructure; see Architecture tab. | Fixed - Pending Deploy | 2026-08-11 | Also found or a stray nginx risk: old .bak config files were sitting inside sites-enabled/ and being parsed as duplicate server blocks (include sites-enabled/* has no extension filter) — moved to /etc/nginx/backups/.
20 | Sales Helper Agent | 1) Assistant chatbot should open on the right side like other AI agent panels, with a background that doesn't blend into the page. 2) Close button isn't visible. | Users may not realize the chatbot is open, can't tell where its edges are against the page background, and can't figure out how to dismiss it. | Major | Not yet started — needs frontend/src/agents/SalesHelperAgent.js + styles/SalesHelperAgent.css panel positioning/z-index/close-button audit. | Reposition to a right-docked panel consistent with other agent chat surfaces; give it a distinct surface color from --color-background; ensure the close control has visible contrast and a hit target. | Pending | 2026-08-11
21 | Supply Chain Audit | Should have a Market-Research-style flow: enter Project context & description, Industry, Region to get a supplier list. | Right now Supply Chain Audit is pure manual data entry (submit a name + a numeric score) with no AI-assisted discovery step — inconsistent with how Market Research works, and arguably not doing anything “AI” at all today. | Major | backend/agents/supply_chain/service.py submit_audit() just thresholds a user-typed score (>=70 = passed). No LLM/AI call anywhere in the file — confirmed via full-file review. There is no supplier-discovery endpoint to reuse the way RequirementsGathering.js reuses search-google-businesses. | Two-part fix: (1) UX — add the same context/industry/region input pattern used in Market Research; (2) backend — this needs a real supplier-discovery capability (e.g. reuse the Google Places search already built for Market Research, or a dedicated LLM-assisted supplier search), not just a form. Not started. | Pending | 2026-08-11 | See Architecture tab: Supply Chain Audit currently has zero AI involvement despite being marketed as an agent.
22 | Email Outreach | When a lead list from Market Research is loaded into Email Outreach, the Send button doesn't activate. | User does the work of researching leads, but can't act on them in the next step — breaks the Market Research → Email Outreach handoff that's supposed to be the point of having both agents. | Blocker | Not yet started — needs frontend/src/agents/EmailOutreachAgent.js Send-button enable condition traced against the shape of a lead list loaded from Market Research (likely a field-name/shape mismatch between what Market Research saves and what Email Outreach's validation expects). | Trace the Send button's disabled= condition and compare the loaded list's shape against what it checks for; likely needs to accept the Market-Research lead shape directly instead of expecting a different field name. | Pending | 2026-08-12
23 | Agents Assembly | AI Chat doesn't respond to queries — shows “Error contacting chat API.” | The floating business-context chat assistant on the main agent-browsing page is completely non-functional. | Blocker | ROOT-CAUSED TODAY: frontend/src/components/AgentsAssembly.js:402 calls axios.post('/enterprise_chat', ...) with no Authorization header. backend/app.py:4021-4024 has @require_auth on that route → always 401. Same bug class as the Market Research/Email Outreach missing-auth-header sweep from earlier this session, missed then because that sweep only searched for fetch(...) calls — this file uses axios instead. Also found: AgentsAssembly.js:458 axios.post('/recommend_agents', ...) has the exact same missing-header problem (backend/app.py:5334-5336, also @require_auth). | Add the Authorization header (authJsonHeaders()) to both axios calls in AgentsAssembly.js (lines ~296, 402, 458 — the 3rd, axios.get('/search_businesses'), has a different problem: that route doesn't exist in the backend at all, see notes). | Pending | 2026-08-19 | /search_businesses (AgentsAssembly.js:296) is a 4th, separate bug: the backend has no such route (confirmed via grep) so this call 404s on every keystroke in the search/industry filter. It fails silently today (empty array, no visible error) so it's not user-blocking, but it's dead weight worth removing or wiring to a real endpoint.
24 | Agents Assembly | 1) First-time users should land on the agent grid; returning users with projects should land on the Dashboard. 2) AI Assistant should default open on the right, Copilot-style. 3) A Search Agents bar above the grid should recommend agents as the user types. | New users are dropped into whichever landing page regardless of whether they have any history; there's no adaptive “what should I do first” guidance; and there's no way to describe your goal in plain language and get pointed at the right agent — which is the single biggest lever for making 12 agents feel discoverable to a non-technical user instead of overwhelming. | Major | Not started. Two of the three pieces already have backend support to build on: /recommend_agents (backend/app.py:5334) already exists and is meant to power exactly this kind of recommendation — it's just broken today (see AI Chat bug above) and not wired to a persistent search bar. | (1) Branch the landing route on whether the user has any projects/workflow history. (2) Design decision needed: an always-open right panel is a bigger UX commitment than the current click-to-open chat — confirm before building. (3) Build a search-as-you-type bar that calls /recommend_agents (once its auth bug is fixed) and surface top matches inline. | Pending | 2026-08-19
25 | Workflows | Workflow process should be: set business context → create project → configure workflow, with AI recommending/configuring suitable agents per stage, plus dependency management to allow/restrict agent configuration based on what a stage depends on. | This describes real orchestration — automatic agent selection and hand-off. Today's Workflows feature does not do this: it's a manual checklist where a human runs each agent by hand and clicks “complete stage” themselves; no agent is ever invoked automatically and no stage's output is piped into the next stage's input automatically. | Major | backend/models/workflow.py advance_stage() only does bookkeeping (marks stage complete, merges whatever data the human already saved, increments an index) — confirmed by direct code read. docs/context.md already self-diagnoses this exact gap under 'Current Limitations (Potential LangGraph Migration)'. | This is the single clearest case for LangGraph/Temporal adoption in the whole codebase — see Architecture tab for the full recommendation and a phased plan. Not a small fix; needs a design pass before implementation. | Pending | 2026-08-19 | Directly duplicates/extends docs/context.md line 378 and docs/todo.md line 741, both already flagged internally but not actioned.
26 | Workflows | After clicking “Start Workflow,” the UI should look like the attached reference image. | Can't verify against the referenced Google Drive image (not accessible from this environment) — but the direct-navigation-into-runner behavior was already improved earlier this session (Start Workflow now lands the user straight in the WorkflowRunner instead of a list with contradictory started/not-started messaging), which may already address part of this. | Minor | Needs the reference image to know what's actually still different from current behavior. | Please attach the image directly (Drive links aren't fetchable from this environment) or describe the specific difference so it can be scoped. | Needs Clarification | 2026-08-19
27 | Dashboard / Welcome | “Start a Workflow” template card's “Start workflow” button navigates to /workflows?template=ID, but the Workflows page never reads that param — the user's chosen template is silently dropped and they land on the generic template list. | Button doesn't do what it visibly promises — user picked a specific workflow and has to find and click it again. | Major | frontend/src/pages/Dashboard.js:138 sets ?template=; frontend/src/workflows/WorkflowsPage.js never reads it (confirmed via grep, no useSearchParams/get('template') usage). | Read the template query param on WorkflowsPage mount and either auto-scroll to / highlight that template card, or open its start flow directly. | Pending | 2026-08-22
28 | Navigation / Routing | No catch-all 404 route, and 2 agents' catalog routes don't match their real mounted routes: aiChatbot is configured as /ai-chatbot but actually mounted at /aichatbot; teamPerformance's /team-performance isn't registered in App.js at all. A ROUTE_REDIRECTS safety-net map exists in agentsConfig.js but App.js never imports or uses it. | Today these 2 agents are hidden from the visible catalog, so the practical blast radius is low — but agentsConfig.js is documented as the 'single source of truth,' and anyone building a new entry point (search, deep link, un-hiding an agent) off that config hits a silent blank white page with no error and no way back except browser Back. | Minor | frontend/src/config/agentsConfig.js:145 (aiChatbot route) vs App.js:72 (actual mount at /aichatbot); agentsConfig.js:159-166 (teamPerformance, no matching App.js route); agentsConfig.js:244-252 (dead ROUTE_REDIRECTS map). | Fix the route string mismatch for aiChatbot; either register /team-performance or remove it from the config until built; add a real <Route path="*"> catch-all that shows a proper “page not found, go to Dashboard” screen instead of a blank one. | Pending | 2026-08-22
29 | Market Research | “Connect Google Business Account” modal asks for a raw Client ID and Redirect URI with placeholder text only — no explanation, no link to where to get these values. | These are developer/OAuth-setup terms. A non-technical business user cannot complete this step — it's a hard stop on a real task, not just confusing. | Blocker | frontend/src/agents/RequirementsGathering.js:2212-2232. | Either fully hide this behind an admin/settings-only surface (most users should never need to see raw OAuth fields) or add inline help text + a “how to get this” link right in the modal. | Pending | 2026-08-22
30 | Agents Assembly | The agent catalog page (AgentsAssembly.js) maintains its own hardcoded list of 9 agents, completely independent of config/agentsConfig.js (which defines 12, and is documented elsewhere as the source of truth). | Any future edit to an agent's price, description, or status in the “source of truth” config silently fails to show up on the actual page users browse from — the two lists can (and likely already do, subtly) drift apart. | Major | frontend/src/components/AgentsAssembly.js:179-289 defines its own businessModules/technicalModules; only Projects.js and Dashboard.js actually import from agentsConfig.js. | Make AgentsAssembly.js render from getAllAgents() in agentsConfig.js instead of its own parallel array; reconcile any fields present in one but not the other before switching. | Pending | 2026-08-22
31 | Executive Assistant | Catalog description promises stakeholder coordination “via WhatsApp” and lists “WhatsApp Integration” as a feature, but the actual agent only sends email reminders — no WhatsApp anywhere in the implementation. | A user picks this agent expecting WhatsApp messages and gets email instead — a straightforward false-advertising bug, not a hypothetical. | Major | config/agentsConfig.js:99,103 (“WhatsApp”) vs agents/ExecutiveAssistantPage.js:332,352 (email-only, confirmed in both copy and implementation). | Update the catalog description/feature list to say email, or actually add WhatsApp support if that's the real intent — needs a product decision, not just a copy fix. | Pending | 2026-08-22
32 | Cross-agent | Error toasts routinely show raw technical internals to business users: “invalid JSON response from server,” “chunks/entities” counts, raw JS exception text via `+ error.message`. | Directly violates the platform's own stated design principle (docs/context.md: “Business-friendly language only — no technical jargon”). A user sees words like “JSON,” “server,” “chunks” with no idea what any of it means or what to do next. | Major | Pattern repeats across agents/RequirementsGathering.js (7+ call sites, e.g. line 1148 ‘invalid JSON response from server’), agents/DataInsights.js:439,659 (‘X chunks, Y entities’, raw error.message), and others. | Introduce a shared error-translation layer: map known backend error codes/messages to plain-language copy, and never interpolate a raw exception message directly into a user-facing toast as the primary text (log it to console instead). | Pending | 2026-08-22
33 | Executive Assistant / Supply Chain | Both agents skip the AgentOutcomesStrip intro (“what this does / what you'll get”) that every other ready agent shows, dropping straight into empty form fields. | Inconsistent onboarding — two agents give business users no orientation before asking them to fill in fields, unlike their siblings. | Minor | Confirmed via import list: agents/EmailOutreachAgent.js and agents/SupplyChainAgent.js never import AgentOutcomesStrip. | Add the same AgentOutcomesStrip block used by the other 9 agent pages. | Pending | 2026-08-22
34 | Cross-agent | The same underlying concept is asked for or labeled differently depending on which page you're on: “Business Context” (Settings), “Project context & description” (Market Research), “Context/Instructions” (Content Marketing), “Project Context” (Executive Assistant) — and “Industry” is asked in 3 unsynced places (Settings, the Agents Assembly filter dropdown, and the floating chat widget), each with its own separate answer that never reconciles with the others. | A user who already told the app their industry in Settings gets asked again by the chat widget and again by a filter dropdown, with no acknowledgment — reads as “this app doesn't remember anything about me,” and reinforces that the platform is a set of separate tools bolted together rather than one coherent product. | Minor | Settings.js Business Context tab; RequirementsGathering.js:1710; ContentMarketingAgent.js:645; ExecutiveAssistantPage.js:394; AgentsAssembly.js:974-988 (filter) and :385-456 (chat widget, separate local state). | Establish one canonical “business context” record (Settings already half-owns this) and have every other surface read/prefill from it instead of asking fresh each time. | Pending | 2026-08-22
35 | Agents Assembly | “Process” filter (Sales, Procurement, HR, Operations, Finance, Customer Service) and the chat widget's “Department” list (15 different options, different set) describe the same real-world concept with two different vocabularies on the same page. | Minor confusion — a user who picks “Procurement” in the filter may not realize the chat widget calls the same idea something else with a different, longer list. | Minor | AgentsAssembly.js:994-1000 (filter) vs AgentsAssembly.js:22-24 (chat departmentOptions). | Reconcile to one shared vocabulary/option list used by both surfaces. | Pending | 2026-08-22
36 | Email Outreach | Compose field hint text says “Use {{variable}} syntax for personalization” with no picker — requires knowing template-notation syntax. | Business users writing outreach emails shouldn't need to know what “syntax” or curly-brace templating is. | Minor | agents/EmailOutreachAgent.js:312-314. | Replace the raw-notation hint with an “Insert field” dropdown/button that inserts the token for the user. | Pending | 2026-08-22
37 | Header | “System Overview” modal (~150 lines of wired-up state: tools landscape, business context wizard, recommended agents) has no remaining caller — both icons that used to open it are commented out as hidden. | Not user-facing today (unreachable), but dead, maintained-looking complexity that risks confusing whoever next touches Header.js into thinking it's live. | Minor | core/Header.js:425-747 (handleSystemClick + modal), icons commented out at lines 492-515. | Delete the dead code, or deliberately re-surface it if there's a plan to bring it back. | Pending | 2026-08-22
38 | Invest Agent | Coming-soon stub renders 11 disabled inputs labeled generically “Parameter 1” … “Parameter 11.” | Reads as a broken form at a glance rather than an intentional coming-soon state. | Minor | agents/InvestAgent.js:4,21-27. | Replace with a simple “coming soon, notify me” state instead of 11 meaningless disabled fields. | Pending | 2026-08-22

## Architecture & Agent Quality
Architecture & Agent Quality Assessment
Answers: are these actually AI agents, is the orchestration solid, and do we need LangGraph/Temporal? Based on a full read of backend/agents/*, app.py, models/workflow.py, routes/workflows.py, and cross-checked against docs/context.md's own prior audit notes.
# | Area | Current State (Finding) | Why It Matters | Recommendation | Priority | Effort
1 | Overall verdict | Every 'agent' that calls an LLM does so via one hardcoded, sequential prompt→completion round trip (occasionally 2-4 fixed steps, e.g. the knowledge-graph builder). There is no code path anywhere in the backend where the LLM's own output decides the next action — no planning, no self-correction, no dynamic tool selection, no multi-agent handoff. This is LLM-templated API endpoints, not agentic architecture. | Sets expectations correctly: today's platform is a strong collection of point features powered by AI, not a system of autonomous agents. That's not inherently bad — many of these tasks (research, drafting, scoring) don't need autonomy — but the marketing language ('AI agent' x12) and the Workflows feature's design both imply more autonomy than exists. | Either dial back 'agent' framing to match reality for the simple ones, or selectively invest in real orchestration where it earns its keep (see Workflows row below) rather than everywhere uniformly. | P1 | Discussion
2 | Agents with zero AI/LLM involvement | Executive Assistant (task/reminder CRUD only), Supply Chain Audit (thresholds a user-typed numeric score), and Event Networking's recommendation engine (pure keyword overlap, explicitly commented as non-LLM) have no LLM call anywhere in their backend code — confirmed by full-file grep for ai_chat_completion/openai in each. | These 3 are marketed and labeled identically to genuinely AI-powered agents. A user who tries Supply Chain Audit expecting AI-assisted supplier discovery (which the pending xlsx feature request explicitly asks for) gets a manual scoring form. | Short term: be explicit in-product about what's automated vs manual per agent. Medium term: Supply Chain Audit and Event Networking's recommender are the two best near-term candidates to actually add LLM/RAG value (reuse the Market Research Google Places search pattern for Supply Chain; add semantic matching to Event Networking). | P1 | Medium (per agent)
3 | Workflows do not orchestrate agents | backend/models/workflow.py advance_stage() only does bookkeeping (marks a stage complete, merges whatever data a human already saved via the agent page, increments an index). No agent is ever invoked programmatically. A 'workflow' today is a manual checklist across independent agent pages, not a pipeline. | This is the platform's single named 'orchestration' feature, and it's the top complaint in this session's UX feedback ('workflow doesn't feel intuitive... where should I go next'). The disconnect between what Workflows implies (automated multi-agent pipeline) and what it does (progress tracker) is very likely the root of that confusion, not just a labeling/UI issue. | This is the clear, high-value case for LangGraph: model each workflow as a graph of agent nodes with shared state, let stage N's output feed stage N+1's input automatically, support conditional branching and human-in-the-loop approval gates. docs/context.md already reaches this same conclusion independently ('Current Limitations (Potential LangGraph Migration)') — it's a known, previously-flagged gap that hasn't been actioned. | P0 | Large
4 | Temporal vs LangGraph for Workflows | Two different problems get conflated under 'orchestration': (1) composing several LLM/agent calls with shared state and conditional routing — LangGraph's job; (2) durable execution of a long-running, possibly-paused, possibly-failing process with retries and resumability — Temporal's job. Workflows today are also frequently long-running in wall-clock time (a human does stage 1, comes back hours/days later for stage 2) and already have pending/running/paused states in the DB model, which is closer to Temporal's problem shape. | Picking the wrong tool means paying integration cost twice. LangGraph alone doesn't give you durable, crash-safe, resume-after-days execution; Temporal alone doesn't give you a natural graph-of-agents authoring model. | Recommended split: use LangGraph (in-process, lighter weight, already has langchain as a sibling dependency) to define how a single workflow *stage* invokes its agent, including any multi-step reasoning within that stage. Keep Temporal on the shortlist only if/when workflows need guaranteed durability across days/infra restarts and human-approval waits — don't adopt both at once. Start with LangGraph; it directly targets the gap that's actually blocking users today. | P0 | Large (design spike first)
5 | Celery is mostly decorative | 5 tasks.py files exist (market_research, content_marketing, email_outreach, supply_chain, document_intelligence). 3 of the first 4 contain literal '# TODO' stub bodies that do nothing but flip a DB status field and are never actually triggered by any reachable frontend code path. Only document_intelligence has real Celery usage: retries (max_retries=3), SSE-style progress notifications, and a polled status endpoint. | The exact production incident this session had to band-aid (email enrichment 504 timeout from ~200 businesses processed serially in one HTTP request) is precisely the kind of work Celery already exists to solve — and the infrastructure is half-built and sitting unused for that exact agent. | Wire email_outreach's enrichment (and similarly slow synchronous paths) through the existing Celery pattern already proven in document_intelligence: enqueue → return immediately → frontend polls status — instead of extending timeout/cap band-aids further. | P1 | Medium
6 | Content Marketing route-shadowing bug | backend/agents/content_marketing/routes.py (a properly migrated blueprint with service.py) is registered AFTER identically-pathed legacy @app.route handlers directly in app.py. Flask matches the first-registered rule, so the app.py versions silently win and the 'migrated' blueprint code (including a real FAISS-backed RAGContentGenerator that's otherwise unused) is dead, unreachable code. | Anyone who edits service.py believing they're fixing live behavior is wasting effort — changes never take effect. This is a maintainability trap, not a user-facing bug today. | Remove the duplicate app.py routes (or the unused blueprint, whichever is intended to be canonical) and actually wire up RAGContentGenerator, which appears to be more capable than what's live. | P2 | Small
7 | No retry/backoff around LLM calls | core/ai_client.py's ai_chat_completion has no explicit timeout or retry wrapper — relies entirely on the underlying OpenAI/Anthropic SDK defaults. Nearly every route wraps its logic in a single broad try/except Exception → 500 with the raw exception string. | A transient LLM API blip becomes a hard user-facing failure instead of a silent, invisible retry — directly undermines reliability for a product whose entire value proposition is 'the AI works.' | Add a shared retry/backoff wrapper (e.g. tenacity, already likely available given langchain's dependency tree) around the common LLM-call helper, once, centrally. | P1 | Small
8 | Agent-ID naming collision (still live) | Workflow stage agent id 'market_research' actually routes to the Data Insights agent, not the Market Research agent (frontend/src/workflows/WorkflowRunner.js:150-153, confirmed live in code today). This was flagged as a P0 'must fix before production' item in docs/todo.md back in July 2026 and is still unresolved 3+ weeks later. | Anyone (developer, or the AI-recommends-agents feature requested elsewhere in the tracker) reasoning about workflow templates from the ID alone will misroute. It's currently papered over with a route/label override, not actually fixed at the data-model level. | Rename the agent id from market_research to data_insights everywhere it's referenced (WorkflowRunner.js, backend/config/workflow-templates/*.json) in one atomic change with a full workflow-template regression test, since docs/todo.md already scoped exactly this. | P1 | Small (well-scoped already in docs/todo.md)
9 | Missing-auth-header bug class recurs | This session fixed ~16 endpoints missing Authorization headers, all found via a regex sweep of fetch() calls. Today's audit found 3 more identical bugs in AgentsAssembly.js — missed because that file uses axios instead of fetch, so the earlier sweep's search pattern didn't catch it. | The bug class itself (developer forgets the shared auth-header helper) is systemic, not isolated — shows up wherever a call site doesn't go through one enforced wrapper. | Introduce a single authenticated HTTP client (thin wrapper around fetch or axios, used everywhere) so auth headers are structural, not a convention that has to be remembered per call site; would have prevented all ~19 instances of this bug class. | P1 | Medium
10 | Agentic UX honesty | Given the above, a non-technical user's actual experience per agent varies widely: Market Research (real search + real generation) and Data Insights (real RAG) deliver on the 'AI agent' promise; Executive Assistant and Supply Chain Audit currently don't use AI at all despite the framing. | Directly answers the question 'will a non-technical user really be able to use the app well': for the AI-powered agents, yes — the UX issues found in this audit (jargon leakage, inconsistent onboarding, terminology drift) are real but fixable polish, not fundamental blockers. For the non-AI-labeled-as-AI agents and for Workflows specifically, the gap is between what's promised and what's delivered, which erodes trust faster than a rough edge would. | Prioritize: (1) fix the Workflows orchestration gap (biggest UX complaint, now has a concrete architectural answer), (2) close the jargon/error-message leaks already flagged in Sheet 1 (directly contradicts the platform's own written design principle), (3) be honest in-product about which agents are AI-assisted vs manual today rather than waiting for all of them to be true agents. | P0 | —